## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | DLWMS | https://www.fit.ba/student/login.aspx
Program Manager | Amar Alić, Kenan Alić, Dženan Magrdžija
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Input polje "Pretraga obavijesti...": Nakon što u input polje "Pretraga obavijesti..." na početnoj stranici upišemo: "rezultati 2", ne prikaže nam to što smo tražili, već dobijemo pogrešne formate obavijesti.Uopšte nam ne prikazuje sve pojmove koji sadrže te riječi, već pojmove iz 2016. godine i starije. Očekivano: očekivali smo da će biti prikazane sve obavijesti koje u svom nazivu imaju riječ "rezultati" i/ili broj "2". |  | Post-Deployment | Medium |  |  |  | New |  |  |  |  | New
2 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Ključne riječi u arhivi dokumenata: Kada upišemo bilo koju riječ za bilo koji predmet u arhivi dokumenata i kliknemo dugme "Traži", pretraga nam ne vraća dokumente sa ključnom riječju koja je unešena, odnosno nikakve rezultate. Očekivano: nakon upisa ključne riječi ili više njih, da dobijemo ispravne rezultate pretrage pritiskom na button "Traži". |  | Post-Deployment | Low |  |  |  | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Arhiva obavijesti objavljenja u periodu od do: Nakon klika na link "Arhiva" na početnoj stranici, dozvoljen je unos veće godine prema manjoj u input polja za datum, odnosno većeg datuma prema manjem, gdje nakon pritiska na button "Traži", osvježi stranicu i ispiše "Nema rezultata pretrage." Očekivano: Da dobijemo obavijest kako nije moguće da se unese veći datum prema manjem. |  | Post-Deployment | Medium |  |  |  | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Nastava -> izbor predmeta: Nakon što uđemo na stanicu "Nastava" i odemo na link "Izbor predmeta", kada isključimo "Označi sve" i označimo nekoliko predmeta i kliknemo button "Sačuvaj", te se zatim ponovo vratimo na "Izbor predmeta", "Označi sve" je ponovo čekirano iako ranije nije bilo odabrano. Očekivano: Nakon spašavanja promjena koje smo željeli da spasimo i ponovo se vratimo da provjerimo odabrane predmete, treba da budu odabrani samo oni koje smo ranije i spasili. |  | Post-Deployment | Low |  |  |  | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Predmeti u combo-boxu: Nakon što uđemo na stranicu "Nastava" i na linku "Izbor predmeta" odaberemo samo nekoliko predmeta i pri tome nije označeno "Označi sve", te pritisnemo na button "Sačuvaj", u combo-boxu pod nazivom "Predmet" na stanici "Nastava", i dalje su prikazani svi predmeti a ne samo oni koji su označeni ranije. Očekivano: Da budu prikazani samo oni predmeti koji su označeni odnosno odabrani i spašeni ranije. |  | Post-Deployment | Low |  |  |  | New | [6 empty] | Executing/Controlling | Design
6 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Raspored nastave: Nakon što uđemo na stanicu "Nastava" i odaberemo bilo koji predmet, te kliknemo na link "Raspored nastave", ne dobijamo ispravne povratne informacije niti za jedan predmet. Očekivano: Da nakon što kliknemo na "Raspored nastave" za željeni predmet, dobijemo ispravne povratne informacije o rasporedu nastave. |  | Post-Deployment | Low |  |  |  | New | [6 empty] | Closing | Development
7 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Termini: Nakon što uđemo na stranicu "Termini" i želimo da prijavimo ispitne rokove, redovan student može da prijavi ispitne rokove za apsolvente iako nije apsolvent. Očekivani rezultati: Da dobijemo notifikaciju da nismo apsolventi i da ne možemo prijaviti apsolventske ispitne rokove. |  | Post-Deployment | High |  |  |  | New | [7 empty] | Testing
8 | 16/01/2024 | Amar Alić, Kenan Alić, Dženan Magrdžija | Profilna slika: Nakon što uđemo na stranicu "Moji podaci", te želimo da postavimo profilnu sliku, za formate: .jpg, .jpeg, .png, dobijemo obavijest da format nije podržan/validan. Očekivani rezultati: Da dobijemo notifikaciju koji je validan format slike i razlog zbog kojeg nije moguće postaviti sliku. |  | Post-Deployment | Low |  |  |  | New | [7 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).